Ciarán Maher 11th-July-2016
KTQ0855

Project Management

# 1.1 Describe three of the principles of project management.
Vision and Mission
In order to be successfully executed, every project should begin with a clear goal firmly in mind. This is effectively accomplished by articulating the Vision and Mission of the project so it is crystal-clear to everyone. Creating a vision and mission for the project helps clarify the expected outcome or desired state, and how it will be accomplished.
Business Objectives
The next step is to establish two to three goals or objectives for the project. Is it being implemented to increase sales and profit, customer loyalty, employee productivity and morale, or product/service quality? Also, it's important to specifically quantify the amount of improvement that is expected, instead of being vague.
Standards of Engagement
Simply put, this means establishing who will be part of the project team? What will be the frequency of meetings? What are the meeting ground rules? Who is the project owner? Who is designated to take notes, and distribute project meeting minutes and action steps? This goes along with any other meeting protocol that needs to be clarified.
# 1.2 Explain three of the benefits of project management.
1. Better Efficiency in Delivering Services: Project management provides a “roadmap" that is easily followed and leads to project completion. Once you know where to avoid the bumps and potholes, it stands to reason that you’re going to be working smarter and not harder and longer.
2. Improved / Increased / Enhanced Customer Satisfaction: Whenever you get a project done on time and under budget, the client walks away happy. And a happy client is one you’ll see again. Smart project management provides the tools that enable this client/manager relationship to continue.
3. Enhanced Effectiveness in Delivering Services: The same strategies that allowed you to successfully complete one project will serve you many times over.
# 1.3 Define what the Mc Kinsey 7S model or SWOT analysis stands for. (Only one of these models is required). For instance, in the case of SWOT, say what the four letters S.W.O.T. represent and show how these four terms may be applied to the above mentioned Fortuna bank by giving a brief example of each term.
A SWOT analysis is a study undertakento examine the Strengths, weaknesses, opportunities and threats that are associated with a situation by considering all the internal and external aspects of the business and market. This way, businesses can understand whether a situation has enough aspects in its’ favour and ultimately worth being pursued.
S(trengths)
- What advantages does your organization have?
- What do you do better than anyone else?
- What unique or lowest-cost resources can you draw upon that others can't?
- What do people in your market see as your strengths?
- What factors mean that you "get the sale"?
- What is your organization's Unique Selling Proposition
Example:
Fortuna Bank has reached a deal with the other main Irish banks to allow it to use their Automatic machine network.

This deal allows Fortuna Bank greater customer reach and satisfaction.

W(eaknesses)
- What could you improve?
- What should you avoid?
- What are people in your market likely to see as weaknesses?
- What factors lose you sales?
Example:
The ATMs will be maintained by the other banks (both in terms of cash and paper for receipts) and their maintenance is beyond the scope of the current project.
Fortuna Bank does not have any direct influence over the maintenance of the ATM machines. This creates a weakness where customer interaction cannot be directly controlled.

O(pportunities)
- What good opportunities can you spot?
- What interesting trends are you aware of?
Example:
Initially, they will launch a pilot program allowing customers from their four Dublin branches to avail of the ATM system. The ATMs will be maintained by the other banks

Once the pilot scheme is completed within the six month designated period, further rollouts to other ATMs should be possible with significantly less investment for development.
Additionally, as the ATMs are maintained by the other banks, this project is vertically scalable to the limit of all ATMs owned by the partnered banks.

T(hreats)
- What obstacles do you face?
- What are your competitors doing?
- Are quality standards or specifications for your job, products or services changing?
- Is changing technology threatening your position?
- Do you have bad debt or cash-flow problems?
- Could any of your weaknesses seriously threaten your business?
Example:
The pilot scheme is expected to be up and running within 6 months, there will be a 6 month maintenance contract thereafter (the cost is included in the initial budget of 50,000).
Beyond the 6 months development period and 6 month maintenance contract; there is no mention of long-term contractual obligations, meaning Fortuna Bank may have invested ~€50,000 and due to the ownership of the ATMs by the other Irish banks; the technological solution may not be relevant beyond the year duration of this project.
# 1.4 Discuss three possible risks to successful completion of projects.
Product size risk i.e. the number of users of the product?
As the number of users increases the cost of producing a product tends to go down, ensuring greater profits. However, if the userbase increases too quickly then necessary infrastructure may fail to meet demand, causing delays and/or cancellations.
Business impact risks i.e. the sophistication of end users?
If a product is not designed in a way that is intuitive to its' intended end users, then the project may ultimately fail
Customer related risks i.e. does the customer understand the software engineering process?
Should a customer become impatient or frustrated with the software development life cycle then an entire project may be cancelled without ever seeing completion.
1.5 Having defined the risks give at least two examples of how to mitigate for risks.
Product size risk i.e. the number of users of the product?
Ensuring the finished product is robust and scalable, will provide the greatest mitigation for this type of risk.
A staged or beta relase schedule can also provide immediate feedback on market penetration and user adoption rates; ensuring anticipation and ultimately mitigation of this type of risk.

Business impact risks i.e. the sophistication of end users?
Ensuring constant feedback from typical end users, at all levels of design stages, will mitigate this risk and ensure project completion.
Thorough care to provide the most intuitive and compelling user experience, by comparing to similar projects; can provide a useful tool for mitigating this type of risk..

Customer related risks i.e. does the customer understand the software engineering process?
Providing regular consultation with customers and other project owners, regarding the current stage of the development process; will provide a clear method of mitigating this risk.
Working to a soft and hard deadline schedule; can ensure that the customer need never experience, let alone understand, the software engineering process. This will minimise the risk even further.
2.1 Briefly define SMART goals which are used to set clear objectives for projects.
SMART Goals
Specific
Well defined
Clear to anyone that has a basic knowledge of the project
Measurable
Know if the goal is obtainable and how far away completion is
Find out when you have achieved your goal
Agreed Upon
Agreement with all the stakeholders what the goals should be
Realistic
Within the availability of resources, knowledge and time
Time-Based
Enough time to achieve the goal
Stressful deadlines which can affect project performance

2.2 In terms of project resource requirements what is a resource?
In terms of project management resource requirements, a resource is required to complete a project task. It could be people, equipment, facilities, funding or anything else capable of definition (usually not including man-hours) required for the completion of the project activity.

2.3 In terms of project communication what does the project manager need to determine?
In terms of project communication, the project manager should determine and then outline a communication plan with the following key elements:

A brief background for the communication plan
This should include the goals, vision and any conclusions of the communication plan.
Stakeholder Analysis
Stakeholder Analysis matrices provides clearer understanding of the various opinions, influences and interests that go into the project that is being managed.
Clearly stated objectives
Clearly laying out what is trying to be achieved with the communication plan and the overall project; is fundamental to circumventing the differences between 'Business Objectives' and 'Communication Objectives'. Utilising the 'SMART' goals paradigm can be the difference between a successful project and a costly, time-wasting project.
The communication strategy
Highlighting a clear communication strategy defines how objectives will be achieved and provides a useful 'sounding-board', ensuring sufficient analysis has been completed and that objectives can be broken down and understood. If the strategy does not come about naturally based on the project objectives and research findings; then the project manager should consider returning to these stages.
Potential issues and risks
Issues management is all about catching problems before they become crises. A well-prepared communication plan should help to prepare for that.

  1. How does a project manager allocate different roles and responsibilities within a project team? A brief description of criteria will be sufficient.
## Areas of Expertise
Expertise/Skill	Responsibilities
Accessibility	Reviews requirements and audits products for 508 compliance. Performs issue management and remediates products when necessary.
Business Analysis	Develops and maintains requirements documentation. Post project, finalize requirements documentation and archive as appropriate.
Change Management	Focuses on changes to business processes, technological function, team roles and responsibilities, organization structures, and the impacts of these changes on budget.
Content Strategy	Responsible for writing content using Plain Language and search optimization techniques, developing content style guides, planning editorial calendars, and creating a sustainable governance model for the site and its stakeholder to follow.
Enterprise Architecture	Focuses on making sure that business mission and information technology assets are aligned. Delivers a system architecture that supports, efficient, adaptable, and a secure environment able to meet the business needs.
Information Architecture	Focuses on creating effective and logical organizational structures that help identify relationships between pieces of content and facilitate the finding of information. Responsible for designing the navigation system, producing the sitemap, defining image/file repository rules, defining naming conventions, and informing wireframing from an information organization point-of-view.
Interaction Design	Uses information about user goals and behavior to design processes and functions that help users interact with the system and achieve their goals. Responsible for identifying those key interactions and wireframing and prototyping them.
Marketing	Focuses on developing inbound and outbound strategies for gaining exposure and attracting intended audiences to the product.
Metrics Analysis	Responsible for the measurement, collection, analysis and reporting of collected data to understand and optimize the usage of and performance related to the product.
Project Management	Develops Project Plan, acquires project resources, and leads kickoff meeting. Oversees project tasks and report project status. Maintain list of Lessons Learned and lead Lessons Learned meeting.
Quality Assurance	Develop QA Plan and audit and report on compliance with the plan. Identify, collect, monitor, and report QA metrics. Participate in and assist others with the execution of QA activities such as walkthroughs, peer reviews, etc.
Subject Matter Expertise	Provides expertise related to the topics, contributes content, and helps verify final product presents factual information.
Technical Development	Responsible for the set-up and maintenance of the content management system, CSS, JavaScript, or other programming related to the site. Should be skilled in developing accessible content and features.
User Research	Responsible for implementing various research methodologies to help gain understanding of user needs and behaviors. Performs the testing, analyzes and reports results, and makes recommendations.
Usability Testing	Focused on evaluating the quality of a user's experience when interacting with a product or system. Tests, analyzes and reports results, and makes recommendations to improve effectiveness, efficiency, and overall satisfaction of the user.
User Interface Design	Focused on creating consistent and predictable interface layouts. Responsible for contributing to the wireframes, prototypes, and navigational elements.
Visual Design	Focuses on the aesthetics of a user interface and any related materials by strategically implementing typography, images, and colors.

Source:
https://www.usability.gov/how-to-and-tools/methods/project-team.html
# 3.1 Why do we use management tools in project management and name at least one commonly used tool.
We use management tools to ensure effective communication and task completion throughout the project. Considering even the smallest of tasks may require two or more teams/team-members, it can quite quickly become unwieldy to organise and co-ordinate resources.

A great open-source example of a commonly used tool that I have experience with is “Trello”

# 3.2 Briefly discuss the possible impact of not using one of these tools.
Not using a project management tool to organise and co-ordinate resources and communication can quite easily result in budgets and deadlines being dramatically overrun. By using a tool such as MS Project, or the above mentioned Trello: which offers a more robust and scalable online solution compared to MS Project; the project manager can constantly monitor deliverables and dependencies which can block progress and intervene to ensure the project stays on budget and meets all expected deadliens within tolerable limits.

# 3.3 Define the critical path of a project.
The critical path of a project can be defined as the most time consuming deliverable of a project plan. This deliverable is critical to the successful completion of the project and is often a dependency for other deliverables of the project plan. As a result, the critical path is the activity which must be completed on time for the project to be completed within the deadline. Any task on the critical path will require the previous task to be completed as they are ultimately dependant on one another. Therefore, if any step of the critical path is delayed; the entire project will invariably be delayed by the same amount of time.
Example:
Given a project involving a new software system; the hardware must be put into place before the software system can be implemented.
# 3.4 For the current ATM system create an overall WBS (Work Breakdown Structure). Define one of the tasks or deliverables needed in one of the categories. For the others, a generic descriptor such as Task B or 2.1 will suffice.
Scenario/context:

Fortuna Bank has reached a deal with the other main Irish banks to allow it to use their Automatic teller machine network. Initially, they will launch a pilot program allowing customers from their four Dublin branches to avail of the ATM system. The ATMs will be maintained by the other banks (both in terms of cash and paper for receipts) and their maintenance is beyond the scope of the current project. Users will be able to check their balances and withdraw money. When they withdraw money, a receipt will be printed. The pilot scheme is expected to be up and running within 6 months, there will be a 6 month maintenance contract thereafter (the cost is included in the initial budget of 50,000).

Post Pilot 1.5
Check deliverables are in line with approved requirements document 1.5.1
Utilising the requirements identified in the approved requirements document previously, ensure all deliverables are confirmed.
  1. Using the WBS (Work Breakdown Structure) create a Gantt chart in Excel which must specify start date, end date and duration of each of the tasks.

See attached Excel document ‘Gantt chart’ sheet.
4.1 Describe a lessons learned document including when and why is it created?
Throughout a project’s life cycle, we learn lessons and discover opportunities for improvement. A lessons learned document allows a clear and concise record of any useful information and mechanisms for future project development. Furthermore documenting lessons learned helps a project team discover both strengths and weaknesses.
It provides an opportunity for team members and/or partners to discuss successes during the project, unintended outcomes, and recommendations for others involved in similar future projects. It also allows the team to discuss things that might have been done differently, the root causes of problems that occurred, and ways to avoid those problems in later project stages.
Use of lessons learned is a principal component of an organisational culture committed to continuous improvement and adaptive management.
Lessons learned mechanisms communicate acquired knowledge more effectively and ensure that beneficial information is factored into planning, work processes, and activities.
The mechanisms or processes used to collect, share, and disseminate lessons learned may vary, but in general such a process is comprised of five main elements: defining the project, collecting information, verifying applicability, storage, and dissemination.

4.2 Using the WBS (Work Breakdown Structure) created above, create a sample chart to review the project against original proposals and say why you would do this.

See attached Excel document ‘Project review’ sheet.

There are many reasons for comparing originally proposed scheduling to actual durations, as it provides many opportunities to improve upon existing development processes; identify areas and techniques to be emulated and potential mistakes which can be corrected or otherwise learned from.